This Amendment is incorporated into the accompanying AIA Document A141™–2014, Standard Form of Agreement Between Owner and Design-Builder dated the «___  » day of  «January  » in the year «2024 » (the “Agreement”)

(In words, indicate day, month and year.)

for the following PROJECT:

(Name and location or address)

Polar Bear – Wilmington Airport, a 500,000 SF distribution center supporting the Life Sciences industry on a 39-acre lot on Gardner Road. in the City of Wilmington, North Carolina  »

«  »

THE OWNER*:

(Name, legal status and address)

«CIL ILM, LLC  »«  »

«805 N. 23rd St.

Wilmington, NC 28405    »

*The term “Owner” is used by the parties for convenience given the standard wording in this Agreement. The parties acknowledge CIL ILM, LLC is not the fee owner of the property at which the Project is to be constructed but, instead, is a ground lessee at the same.

THE DESIGN-BUILDER:

(Name, legal status and address)

«Evans General Contractors, LLC »

«3050 Northwinds Parkway

Suite 200

Alpharetta, GA 30009»

The Owner and Design-Builder hereby amend the Agreement as follows.

TABLE OF ARTICLES

A.1	CONTRACT SUM

A.2	CONTRACT TIME

A.3	INFORMATION UPON WHICH AMENDMENT IS BASED

A.4	DESIGN-BUILDER’S PERSONNEL, CONTRACTORS AND SUPPLIERS

A.5	COST OF THE WORK

# ARTICLE A.1   CONTRACT SUM

§ A.1.1 The Owner shall pay the Design-Builder the Contract Sum in current funds for the Design-Builder’s performance of the Contract after the execution of this Amendment. The Contract Sum shall be one of the following:

(Check the appropriate box.)

[ «  » ]	Stipulated Sum, in accordance with Section A.1.2 below

[ «  » ]	Cost of the Work plus the Design-Builder’s Fee, in accordance with Section A.1.3 below

[ «X» ]	Cost of the Work plus the Design-Builder’s Fee with a Guaranteed Maximum Price, in accordance with Section A.1.4 below

(Based on the selection above, complete Section A.1.2, A.1.3 or A.1.4 below.)

§ A.1.2 Stipulated Sum – Intentionally Omitted

§ A.1.3 Cost of the Work Plus Design-Builder’s Fee – Intentionally Omitted

§ A.1.4 Cost of the Work Plus Design-Builder’s Fee With a Guaranteed Maximum Price

§ A.1.4.1 The Cost of the Work is as defined in Article A.5, Cost of the Work.

§ A.1.4.2 The Design-Builder’s Fee:

(State a lump sum, percentage of Cost of the Work or other provision for determining the Design-Builder’s Fee and the method for adjustment to the Fee for changes in the Work.)

« five percent (5%) of the Cost of the Work »

§ A.1.4.3 Guaranteed Maximum Price

§ A.1.4.3.1 The sum of the Cost of the Work and the Design-Builder’s Fee is guaranteed by the Design-Builder not to exceed «Eighty-Two Million, Seven Hundred Thirteen Thousand, Seven Hundred Eighty-Six Dollars  » ($«82,713,786.00»), subject to additions and deductions for changes in the Work as provided in the Design-Build Documents. Costs that would cause the Guaranteed Maximum Price to be exceeded shall be paid by the Design-Builder without reimbursement by the Owner.

(Insert specific provisions if the Design-Builder is to participate in any savings.)

« Should the Cost of the Work Plus Design-Builder’s Fee be less than the final Guaranteed Maximum Price, 25% of the savings (savings defined as the final Guaranteed Maximum Price minus the Cost of the Work Plus Design-Builder’s Fee) shall be paid to Design-Builder as additional fee, Owner retaining the other 75% of the savings.  »

§ A.1.4.3.2 Itemized Statement of the Guaranteed Maximum Price

Provided below is an itemized statement of the Guaranteed Maximum Price organized by trade categories, allowances, contingencies, alternates, the Design-Builder’s Fee, and other items that comprise the Guaranteed Maximum Price.

(Provide information below or reference an attachment.)

« see the Schedule of Values attached to the Agreement as Exhibit F. »

§ A.1.4.3.3 The Guaranteed Maximum Price is based on the following alternates, if any, which are described in the Design-Build Documents and are hereby accepted by the Owner:

(State the numbers or other identification of accepted alternates. If the Owner is permitted to accept other alternates subsequent to the execution of this Amendment, attach a schedule of such other alternates showing the change in the Cost of the Work and Guaranteed Maximum Price for each and the deadline by which the alternate must be accepted.)

«Not Applicable.  »

§ A.1.4.3.4 Unit Prices, if any: Not Applicable.

§ A.1.4.3.5 Assumptions, if any, on which the Guaranteed Maximum Price is based:

« see the Design-Builder’s Clarifications attached to the Agreement as Exhibit E. »

§ A.1.5 Payments

§ A.1.5.1 Progress Payments

§ A.1.5.1.1 Based upon Applications for Payment submitted to the Owner by the Design-Builder, including all supporting documentation reasonably requested of the Design-Builder by the Owner, the Owner shall, upon its determination that the Work or a portion of the Work, as applicable, has been completed in a manner consistent with the Design-Build Documents and applicable law, make progress payments of undisputed amounts on account of the Contract Sum to the Design-Builder as provided below and elsewhere in the Design-Build Documents.

§ A.1.5.1.2 The period covered by each Application for Payment shall be one calendar month ending on the last day of the month.

§ A.1.5.1.3 All Applications for Payment shall show the percentage of completion of each portion of the Work as of the end of the period covered by the Application for Payment.  Provided that an Application for Payment is received not later than the «last» day of the month, the Owner shall make payment of the certified amount to the Design-Builder not later than the «last» day of the «following» month. If an Application for Payment is received by the Owner after the application date fixed above, payment shall be made by the Owner not later than «thirty» ( «30» ) days after the Owner receives the Application for Payment, subject to the terms and conditions of this Agreement and the other Design-Build Documents.

(Federal, state or local laws may require payment within a certain period of time.)

§ A.1.5.1.3.1  Each Application for Payment shall be accompanied by the following, all in form and substance satisfactory to the Owner and in compliance with applicable law of the State of North Carolina:

.1   Executed conditional waivers or releases of mechanics and material and equipment suppliers liens from the Design-Builder and all applicable Contractors, Subcontractors, Sub-subcontractors and material and equipment suppliers;

.2  Such other supporting information, documentation and materials as the Owner shall reasonably require, provided at least fifteen (15) days advance notice of the Owner’s requirements is provided; and

.3 the current construction schedule for the Work approved by Owner for the Project in a format agreed to by the Owner and the Design-Builder.

§ A.1.5.1.4 With each Application for Payment where the Contract Sum is based upon a Stipulated Sum or Cost of the Work with a Guaranteed Maximum Price, the Design-Builder shall submit the most recent schedule of values in accordance with the Design-Build Documents. The schedule of values shall allocate the entire Contract Sum among the various portions of the Work. Compensation for design services, if any, shall be shown separately. Where the Contract Sum is based on the Cost of the Work with a Guaranteed Maximum Price, the Design-Builder’s Fee shall be shown separately. The schedule of values shall be prepared in such form and supported by such data to substantiate its accuracy as the Owner reasonably may require. This schedule of values, unless objected to by the Owner, shall be used as a basis for reviewing the Design-Builder’s Applications for Payment.

§ A.1.5.1.5 In taking action on the Design-Builder’s Applications for Payment, the Owner shall be entitled to rely on the accuracy and completeness of the information furnished by the Design-Builder and shall not be deemed to have made a detailed examination, audit or arithmetic verification of the documentation submitted in accordance with Sections A.1.5.1.4, or other supporting data; to have made exhaustive or continuous on-site inspections; or to have made examinations to ascertain how or for what purposes the Design-Builder has used amounts previously paid. Such examinations, audits and verifications, if required by the Owner, will be performed by the Owner’s auditors acting in the sole interest of the Owner and shall not relieve the Design-Builder of any of the Design-Builder’s obligations under the Design-Build Documents.

§ A.1.5.1.6 Except with the Owner’s prior approval, the Design-Builder shall not make advance payments to suppliers for materials or equipment which have not been delivered and stored at the site.

§ A.1.5.2 Progress Payments—Stipulated Sum – Intentionally Omitted

§ A.1.5.3 Progress Payments—Cost of the Work Plus a Fee – Intentionally Omitted

§ A.1.5.4 Progress Payments—Cost of the Work Plus a Fee with a Guaranteed Maximum Price

§ A.1.5.4.1 Applications for Payment where the Contract Sum is based upon the Cost of the Work Plus a Fee with a Guaranteed Maximum Price shall show the percentage of completion of each portion of the Work as of the end of the period covered by the Application for Payment. The percentage of completion shall be the percentage of that portion of the Work which has actually been completed.

§ A.1.5.4.2 Subject to other provisions of the Design-Build Documents, the amount of each progress payment shall be computed as follows:

.1	Take that portion of the Guaranteed Maximum Price properly allocable to completed Work as determined by multiplying the percentage of completion of each portion of the Work by the share of the Guaranteed Maximum Price allocated to that portion of the Work in the schedule of values. Pending final determination of cost to the Owner of changes in the Work, amounts not in dispute shall be included as provided in Section 6.3.9 of the Agreement.

.2	Add that portion of the Guaranteed Maximum Price properly allocable to materials and equipment delivered and suitably stored at the site for subsequent incorporation in the Work, or if approved in advance by the Owner, suitably stored off the site at a location agreed upon in writing;

.3	Add that portion of the Guaranteed Maximum Price properly allocable to materials and equipment to be delivered in the next month for which advance payment is requested to comply with the supplier’s payment terms and, also, that portion of the Guaranteed Maximum Price properly allocable to materials and equipment for which deposits are required by the material/equipment suppliers;

.4	Add the Design-Builder’s Fee, less retainage. The Design-Builder’s Fee shall be computed upon the Cost of the Work at the rate stated in Section A.1.4.2 or, if the Design-Builder’s Fee is stated as a fixed sum in that Section, shall be an amount that bears the same ratio to that fixed-sum fee as the Cost of the Work bears to a reasonable estimate of the probable Cost of the Work upon its completion;

.5	Subtract the aggregate of previous payments made by the Owner;

.6	Subtract the shortfall, if any, indicated by the Design-Builder in the documentation required by Section A.1.5.1.4 to substantiate prior Applications for Payment, or resulting from errors subsequently discovered by the Owner’s auditors in such documentation; and

.7	Subtract amounts, if any, for which the Owner has withheld or nullified a payment as provided in Section 9.5 of the Agreement.

Until Design-Builder’s Work is fifty percent (50%) complete, Owner shall have the right to withhold as retainage ten percent (10%) of the progress payment, as calculated under § A.1.5.4.2.1 through § A.1.5.4.2.3, except that Owner shall not withhold retainage on that portion of the progress payment representing payment for: i) Design-Builder’s Fee; ii) completed design services; iii) Design-Builder’s general conditions costs, and iv) Design-Builder’s direct material and equipment purchases. Once Design-Builder’s Work is fifty percent (50%) complete, Owner shall stop withholding retainage from progress payments.

The progress payment amount determined in accordance with this § A.1.5.4.2 shall be further modified under the following circumstances:

.1 Add, with the first Application for Payment following Substantial Completion of the Work, a sum sufficient to increase the total of all progress payments (treating the progress payment then being billed as if paid by Owner) to an amount equal to the Guaranteed Maximum Price less the following: i) Owner’s then-projected savings share; ii) 200% of the estimated cost of the incomplete Work; and

.2 Intentionally deleted.

§ A.1.5.4.3 (1) Acceptable procedures for review and approval of payments to the Architect, Consultants, and Contractors and (2) the percentage of retainage held on agreements with the Architect, Consultants, and Contractors shall be agreed upon by Owner and Design-Builder; and the Design-Builder shall execute agreements in accordance with those terms including the retainage terms of § A.1.5.4.2.

§ A.1.5.5 Final Payment

§ A.1.5.5.1 Final payment, constituting the entire unpaid balance of the Contract Sum, shall be made by the Owner to the Design-Builder when:

|  | .1 |  | the Design-Builder has fully performed the Contract except for the Design-Builder’s responsibility to correct Work as provided in Section 11.2 of AIA Document A141-2017, and to satisfy other requirements, if any, which extend beyond final payment; |
| --- | --- | --- | --- |
|  | .2 |  | the Design-Builder has submitted a final accounting for the Cost of the Work and a final Application for Payment; |
|  | .3 |  | the Design-Builder has submitted (a) all as-built drawings and as-built information related to the Work in PDF and hard copy form, (b) a complete list of Contractors, Subcontractors and principal vendors on the Project, including addresses and telephone numbers, (c) an indexed, loose leaf binder containing complete installation, operation, and maintenance manuals, including all manufacturers’ literature, of equipment and materials used in the Work, (d) an indexed, loose leaf binder containing all inspection reports, permits, and temporary and final certificates of occupancy and licenses necessary for the occupancy of the project, (e) any and all other items required pursuant to the Design-Build Documents to the Owner; |
|  | .4 .5 .6 .7 |  | final lien waivers have been provided by the Design-Builder, the Contractors, the Subcontractors and all material suppliers, conditioned only upon receipt of payments to be made out of the Final Payment; the final inspections by the City of Wilmington Department of Buildings (or equivalent authority) (the ''DOB") and the closure of all open permits affecting the Project pulled by or on behalf of the Design-Builder or Owner ("DOB Acceptance"); a final Certificate for Payment has been issued by the Owner; and all other obligations set forth in Section 9.10 of the AIA Document A141-2017. |

# ARTICLE A.2   CONTRACT TIME

§ A.2.1 Contract Time, as defined in the Agreement at Section 1.4.13, is the period of time, including authorized adjustments, for Substantial Completion of the Work.

§ A.2.2 The Design-Builder shall achieve Substantial Completion of the Work as follows:

(Insert number of calendar days. Alternatively, a calendar date may be used when coordinated with the date of commencement. If appropriate, insert requirements for earlier Substantial Completion of certain portions of the Work.)

«

Substantial Completion of the Work - Construction Complete: 357 calendar days from commencement of the Work,

Cooler Validation Complete: 357 calendar days from commencement of the Work,»

, subject to adjustments of the Contract Time as provided in the Design-Build Documents.

§ A.2.3 Liquidated damages

« The Parties agree that the provisions of this Contract concerning the required Substantial Completion Date are material terms of the Contract, the breach of which will entitle Owner to recover damages from Design-Builder to reimburse it for its loss. Due to the uncertainty and difficulty in calculating the loss of revenues and other damages Owner will suffer should Design-Builder fail to timely complete the Project, Owner and Design-Builder mutually agree as follows:

In the event Design-Builder fails to achieve timely Substantial Completion (as that date may be adjusted in accordance with the terms of the Contract), the Owner may assess against the Design-Builder (and its surety) as “Liquidated Damages” and not as a penalty, an amount equal to one thousand dollars ($1,000.00) per day until Substantial Completion has been achieved. However, Liquidated Damages shall not begin to accrue until fourteen (14) calendar days after the required Substantial Completion date.

The Parties agree and understand that the amount of Liquidated Damages is reasonable it the Parties’ estimation and that any assessment by Owner of liquidated damages or payment by Design-Builder to Owner of liquidated damages is to compensate Owner for any damages, whether direct or indirect, arising out of Contractor’s delay in achieving the required Substantial Completion Date and that the assessment of Liquidated Damages is intended to be the Owner’s exclusive remedy for any and all damages that arise out of a delay in achieving Substantial Completion but does not waive any other claims Owner may have for any other breach of this Agreement or for defective or improper workmanship, which shall be in addition to any Liquidated Damages.

Furthermore, the Parties agree that regardless of when Design-Builder achieves Substantial Completion of the Work, Design-Builder’s liability for Liquidated Damages to Owner shall not exceed fifty percent (50%) of Design-Builder’s Fee under the Contract.

If and to the extent Owner is entitled to receive Liquidated Damages, Owner may withhold same from any payments that would otherwise be due Design-Builder following the required date of Substantial Completion.

# ARTICLE A.3   INFORMATION UPON WHICH AMENDMENT IS BASED

§ A.3.1 The Contract Sum and Contract Time set forth in this Amendment are based on the following:

§ A.3.1.1 The Supplementary and other Conditions of the Contract: Not Applicable.

§ A.3.1.2 The Specifications:

(Either list the specifications here or refer to an exhibit attached to this Amendment.)

« see the Document Log attached to the Agreement as Exhibit G. »

§ A.3.1.3 The Drawings:

(Either list the drawings here or refer to an exhibit attached to this Amendment.)

« see the Document Log attached to the Agreement as Exhibit G. »

§ A.3.1.4 The Sustainability Plan, if any: Not Applicable.

(If the Owner identified a Sustainable Objective in the Owner’s Criteria, identify the document or documents that comprise the Sustainability Plan by title, date and number of pages, and include other identifying information. The Sustainability Plan identifies and describes the Sustainable Objective; the targeted Sustainable Measures; implementation strategies selected to achieve the Sustainable Measures; the Owner’s and Design-Builder’s roles and responsibilities associated with achieving the Sustainable Measures; the specific details about design reviews, testing or metrics to verify achievement of each Sustainable Measure; and the Sustainability Documentation required for the Project, as those terms are defined in Exhibit C to the Agreement.)

| Title | Date | Pages |
| --- | --- | --- |

Other identifying information:

«  »

§ A.3.1.5 Allowances and Contingencies:

(Identify any agreed upon allowances and contingencies, including a statement of their basis.)

.1 	Allowances

« See Allowance & Contingency List attached to the Agreement as Exhibit H. »

.2 	Contingencies

« See Allowance & Contingency List to the Agreement as Exhibit H »

§ A.3.1.6 Design-Builder’s assumptions and clarifications:

« see the Design-Builder’s Clarifications attached to the Agreement as Exhibit E. »

§ A.3.1.7 Deviations from the Owner’s Criteria as adjusted by a Modification:

« Not Applicable. »

§ A.3.1.8 To the extent the Design-Builder shall be required to submit any additional Submittals to the Owner for review, indicate any such submissions below:

« as required by the Design-Build Documents. »

# ARTICLE A.4   DESIGN-BUILDER’S PERSONNEL, CONTRACTORS AND SUPPLIERS

§ A.4.1 The Design-Builder’s key personnel are identified below:

(Identify name, title and contact information.)

.1	Superintendent

« Jim Smith, Senior Superintendent

3050 Northwinds Parkway, Suite 200

Alpharetta, GA 30009»

Email: j.smith@evans-gc.com

Phone: (404) 561-7456

.2	Project Executive

«

Ron Nestico

4509 Creedmor Road, Suite 401

Raleigh, NC 27612

Email: rnestico@evans-gc.com

Phone: (919) 895-2854 »

.3	Others

« Division Manager:

Sam Holbrook

4509 Creedmor Road, Suite 401

Raleigh, NC 27612

Email: sholbrook@evans-gc.com

Phone: (470) 718-3657   »

§ A.4.2 The Design-Builder shall retain the following Consultants, Contractors and suppliers, identified below:

(List name, discipline, address and other information.)

« as necessary to complete Design-Builder’s Work under the Design-Build Documents. »

# ARTICLE A.5   COST OF THE WORK

§ A.5.1 Cost To Be Reimbursed as Part of the Contract

§ A.5.1.1 Labor Costs

§ A.5.1.1.1 Wages of construction workers directly employed by the Design-Builder to perform the construction of the Work at the site or, with the Owner's prior written approval, at off-site workshops.

§ A.5.1.1.2 Wages or salaries of the Design-Builder's supervisory and administrative personnel for that portion of their time spent in furtherance of Design-Builder’s performance of Design-Builder’s duties under the Design-Build Documents. Unless agreed otherwise, the following standard rates shall apply:

| POSITION | HOURLY RATE |
| --- | --- |
| Project Director | $185.00 |
| Preconstruction Manager | $155.00 |
| Estimating | $95.00 |
| Engineering | $155.00 |
| Design Build Manager | $97.00 |
| Project Executive | $165.00 |
| Senior Project Manager | $115.00 |
| Project Manager | $97.00 |
| Assistant Project Manager | $75.00 |
| Project Engineer | $50.00 |
| Project Coordinator | $65.00 |
| Senior Superintendent | $115.00 |
| Superintendent | $97.00 |
| Assistant Superintendent | $75.00 |
| On-Site Safety | $75.00 |
| Corp Safety Manager | $105.00 |
| Compliance | $185.00 |
| Accounting | $60.00 |
| General Superintendent | $145.00 |

§ A.5.1.1.2.1 The Design-Builder's charge for preconstruction services and design-coordination services in the stipulated sum amount of $85,000.00 to account for time dedicated to preconstruction services and design-coordination services by Design-Builder, the foregoing amount to include amounts billed during the design phase.

§ A.5.1.1.3 Wages and salaries of the Design-Builder's supervisory or administrative personnel engaged at factories, workshops or on the road, in expediting the production or transportation of materials or equipment required for the Work, but only for that portion of their time required for the Work.

§ A.5.1.1.4 Costs paid or incurred by the Design-Builder for taxes, insurance, contributions, assessments and benefits required by law or collective bargaining agreements and, for personnel not covered by such agreements, customary benefits such as sick leave, medical and health benefits, holidays, vacations and pensions, provided such costs are based on wages and salaries previously approved by Owner in writing.

§ A.5.1.1.5 Bonuses, profit sharing, incentive compensation and any other discretionary payments paid to anyone hired by the Design-Builder or paid to the Architect or any Consultant, Contractor or supplier shall not be items of the Cost of the Work.

§ A.5.1.2 Contract Costs. Payments made by the Design-Builder to the Architect, Consultants, Contractors and suppliers in accordance with the requirements of their subcontracts and agreements (including any required deposits), in each case entered into in accordance with this Agreement and the Design-Build Documents.

§ A.5.1.3 Costs of Materials and Equipment Incorporated in the Completed Construction

§ A.5.1.3.1 Costs, including transportation and storage, of materials and equipment incorporated or to be incorporated in the completed construction of the Project; provided, however, that costs incurred for payments for material or equipment in advance of the delivery thereof to the Project site shall be included only if all of the conditions described in Section 9.3.2 of AIA Document A141 -2017 have been satisfied; and provided, further, that payments for all materials stored in any location other than the Project site shall be included only if all conditions described in Section 9.3.2 of AIA Document A141-2017 have been satisfied.

§ A.5.1.3.2 Costs of materials described in the preceding Section A.5.1.3.1 in excess of those actually installed to allow for reasonable waste and spoilage. Unused excess materials, if any, shall become the Owner's property at the completion of the Work or, at the Owner's option, shall be sold by the Design-Builder. Any amounts realized from such sales shall be credited to the Owner as a deduction from the Cost of the Work.

§ A.5.1.4 Costs of Other Materials and Equipment, Temporary Facilities and Related Items

§ A.5.1.4.1 Costs of transportation, storage, installation, maintenance, dismantling and removal of materials, supplies, temporary facilities, machinery, equipment and hand tools not customarily owned by construction workers that are provided by the Design-Builder at the site and fully consumed in the performance of the Work. Costs of materials, supplies, temporary facilities, machinery, equipment and tools that are not fully consumed shall be based on the cost or value of the item at the time it is first used on the Project site less the value of the item when it is no longer used at the Project site. Costs for items not fully consumed by the Design-Builder shall mean fair market value. Any such items not fully consumed which are paid for by the Owner, shall become the property of the Owner and shall be delivered to the Owner upon completion of the Work as required by the Owner in writing.

§ A.5.1.4.2 Rental charges for temporary facilities, machinery, equipment and hand tools not customarily owned by construction workers that are provided by the Design-Builder from an arms-length unrelated third-party equipment rental company at the site and costs of transportation, installation, minor repairs, dismantling and removal. Rates and quantities of equipment owned by the Design-Builder, or a related party shall be subject to the Owner's prior approval The total rental cost of any Design-Builder-owned item may not exceed the purchase price of any comparable item.

§ A.5.1.4.3 Costs of removal of debris from the site of the Work and its proper and legal disposal.

§ A.5.1.4.4 Costs of document reproductions, electronic communications, postage and parcel delivery charges, dedicated data and communications services, teleconferences, Project websites, extranets and reasonable petty cash expenses of the site office.

§ A.5.1.4.5 Costs of materials and equipment suitably stored off the site at a mutually acceptable location, with the Owner's prior approval and provided that all conditions in Section 9.3.2 of AIA Document A141-2017 have been satisfied.

§ A.5.1.4.6 Costs of temporary and or permanent utility consumption expenses (natural gas, water, sewer, electricity) as necessary to complete the Work contemplated by the Agreement. This obligation ceases upon Design-Builder achieving substantial completion. It shall be understood that Owner will provide and or pay for any excess facility charges and or extension fees related to bringing utilities to the property line (if not already there). Design-Builder shall include costs associated with whatever temporary connections, inspections and or facilities required to activate temporary utilities on site.

§ A.5.1.5 Miscellaneous Costs

§ A.5.1.5.1 Premiums for that portion of insurance and bonds required by the Design-Build Documents that can be directly attributed to the Contract. The foregoing notwithstanding, Design-Builder’s liability and workers’ compensation insurance shall be charged at the standard rate of .65% of the Cost of the Work. Design-Builder’s payment and performance bonds shall be charged at the standard rate of 1.25% of the Guaranteed Maximum Price and shall be adjusted when the Guaranteed Maximum Price is increased.

§ A.5.1.5.1.1 Design-Builder shall either bond or enroll in Design-Builder’s Subcontractor Default Insurance Program (“SDI”) all subcontracts and purchase orders. Design-Builder shall charge 1.25% of the Cost of the Work as the cost for such subcontractor bonding or SDI.

§ A.5.1.5.2 Sales, use or similar taxes imposed by a governmental authority that are related to the Work and for which the Design-Builder is liable.

§ A.5.1.5.3 Fees and assessments for the building permit and for other permits, licenses and inspections for which the Design-Builder is required by the Design-Build Documents to pay.

§ A.5.1.5.4 Fees of laboratories for tests required by the Design-Build Documents, except those related to defective or nonconforming Work for which reimbursement is excluded by Section 15.5.3 of the Agreement or by other provisions of the Design-Build Documents, and which do not fall within the scope of Section A.5.1.6.3.

§ A.5.1.5.5 Royalties and license fees paid for the use of a particular design, process or product required by the Design-Build Documents. If such royalties, fees and costs are excluded by the second to last sentence of Section 3.1.13.2 of the Agreement or other provisions of the Design-Build Documents, then they shall not be included in the Cost of the Work.

§ A.5.1.5.6 Costs for electronic equipment and software directly related to the Work.

§ A.5.1.5.7 Deposits lost for causes other than the Design-Builder's negligence or failure to fulfill a specific responsibility in the Design-Build Documents.

§ A.5.1.5.8 Not Used.

§ A.5.1.5.9 Expenses incurred in accordance with the Design-Builder's standard written personnel policy for relocation, and temporary living allowances of, the Design-Builder's personnel required for the Work.

§ A.5.1.5.10 That portion of the reasonable expenses of the Design-Builder's supervisory or administrative personnel incurred while traveling in discharge of duties connected with the Work and that in no event shall such travel include regular commuting.

§ A.5.1.6 Other Costs and Emergencies

§ A.5.1.6.1 Other costs incurred in the performance of the Work (not the subject of another Section of this Amendment pertaining to the Cost of the Work) approved in advance in writing by the Owner.

§ A.5.1.6.2 Costs reasonably incurred in taking action to prevent threatened damage, injury or loss in case of an emergency affecting the safety of persons and property.

§ A.5.1.6.3 Costs of repairing or correcting damaged or nonconforming Work executed by the Design-Builder, Contractors or suppliers, provided that such damaged or nonconforming Work was not caused by negligence or failure to fulfill a specific responsibility of the Design-Builder and only to the extent that the cost of repair or correction is not recovered by the Design-Builder from insurance, sureties, Contractors, suppliers, or others.

§ A.5.1.7 Related Party Transactions

§ A.5.1.7.1 For purposes of Section A.5.1.7, the term “related party” shall mean a parent, subsidiary, affiliate or other entity having common ownership or management with the Design-Builder; any entity in which any stockholder in, or management employee of, the Design-Builder owns any interest in excess of ten percent in the aggregate; or any person or entity which has the right to control the business or affairs of the Design-Builder or any person, or any member of the immediate family of any person, who has the right to control the business or affairs of the Design-Builder. The term “related party” includes any member of the immediate family of any person identified above.

§ A.5.1.7.2 If any of the costs to be reimbursed arise from a transaction between the Design-Builder and a related party, the Design-Builder shall notify the Owner of the specific nature of the contemplated transaction, including the identity of the related party and the anticipated cost to be incurred, before any such transaction is consummated or cost incurred. If the Owner, after such notification, authorizes the proposed transaction, then the cost incurred shall be included as a cost to be reimbursed, and the Design-Builder shall procure the Work, equipment, goods or service from the related party, as a Contractor, according to the terms of Section A.5.4. If the Owner fails to authorize the transaction, the Design-Builder shall procure the Work, equipment, goods or service from some person or entity other than a related party according to the terms of Section A.5.4.

§ A.5.2 Costs Not to Be Reimbursed as Part of this Contract

Notwithstanding anything contained in this Agreement to the contrary, the Cost of the Work shall in no event include the items listed below:

.1	Salaries and other compensation of the Design-Builder's personnel stationed at the Design-Builder's principal office or offices other than the site office, except as specifically provided in Section A.5.1.1;

.2	Bonuses, profit sharing, incentive compensation, and any other discretionary payments, paid to anyone hired by the Design-Builder or paid to any Contractor, Subcontractor or vendor, unless the Owner has provided prior approval.

.3	Expenses of the Design-Builder's principal office and offices other than the site office;

.4	Overhead and general expenses, except as may be expressly included in Section A.5.1;

.5	The Design-Builder's capital expenses, including interest on the Design-Builder's capital employed for the Work;

.6	Costs, fees or expenses due to the gross negligence or willful misconduct of the Design-Builder, any Contractor, any Subcontractors, Sub-subcontractors, their affiliates, and their respective members, partners, directors, employees, agents and/or representatives.

.7    Any cost not specifically and expressly described in Article A.5; and

.8	Costs, other than costs included in Change Orders approved by the Owner, that would cause the Guaranteed Maximum Price to be exceeded.

§ A.5.3 Discounts, Rebates, and Refunds

§ A.5.3.1 Trade discounts, rebates, refunds, and amounts received from sales of surplus materials and equipment shall be credited to the Cost of the Work and shall reduce the Guaranteed Maximum Price and Design-Builder shall use commercially reasonable efforts to make provisions for the securing thereof. The Design-Builder shall take affirmative steps to ensure that it takes full advantage of any and all available discounts, rebates, refunds and returns. All Owner funded cash discounts shall accrue to the Cost of the Work and shall reduce the Guaranteed Maximum Price, and the Design-Builder shall promptly notify the Owner of the availability of such cash discounts in order that the Owner may make funds available therefor. The Design-Builder shall notify the Owner of any discount programs in which the Design-Builder participates that result in future rebates on account of quantity purchases or other factors. To the extent such cost reductions apply to materials or supplies included in the Cost of Work, such reductions shall be credited to the Cost of the Work and shall reduce the Guaranteed Maximum Price, and in the event such rebates occur following Final Payment, the Design-Builder shall remit payment to the Owner for the share of such rebate attributable to the Project.

§ A.5.3.2 Amounts that accrue to the Owner in accordance with Section A.5.3.1 shall be credited to the Owner as a deduction from the Cost of the Work.

§ A.5.4  Other Agreements

§ A.5.4.1 When the Design-Builder has provided a Guaranteed Maximum Price, and a specific bidder (1) is recommended to the Owner by the Design-Builder; (2) is qualified to perform that portion of the Work consistent with the  prevailing applicable professional or industry standards; and (3) has submitted a bid that conforms to the requirements of the Design-Build Documents without reservations or exceptions, but the Owner requires that another bid be accepted, then the Design-Builder may require that a Change Order be issued to adjust the Guaranteed Maximum Price by the difference between the bid of the person or entity recommended to the Owner by the Design-Builder and the amount of the subcontract or other agreement actually signed with the person or entity designated by the Owner. Notwithstanding the foregoing, Design-Builder shall not be required by Owner to contract with any specific party objectionable to Design-Builder for any reason.

§ A.5.4.2 Agreements between the Design-Builder and Contractors shall conform to the applicable payment provisions of the Design-Build Documents, and shall not be awarded on the basis of cost plus a fee without the prior consent of the Owner. If an agreement between the Design Builder and a Contractor is awarded on a cost plus a fee basis, the Design-Builder shall provide in the agreement for the Owner to receive the same audit rights with regard to the Cost of the Work performed by the Contractor as the Owner receives with regard to the Design-Builder in Section A.5.5, below.

§ A.5.4.3 The agreements between the Design-Builder and Architect and other Consultants identified in the Agreement shall be in writing. These agreements shall be promptly provided to the Owner upon the Owner’s written request.

§ A.5.4.4 The Design-Builder shall provide all notices required or permitted by the laws of the State of North Carolina for the protection of the Owner from liens and claims of lien. The Design-Builder shall be responsible for filing in the appropriate court or other governmental office records of all such notices as required or permitted by the laws of the State of North Carolina. The Design-Builder shall provide the Owner with copies of all notices received by the Design-Builder from Contractors, Subcontractors, Sub-subcontractors and material or equipment suppliers for the Project.

§ A.5.5 Accounting Records

The Design-Builder shall keep full and detailed records and accounts related to the Contract Sum and the cost of the Work and exercise such controls as may be necessary for proper financial management under the Contract and to substantiate all costs incurred. The Owner and the Owner’s auditors shall, during regular business hours and upon reasonable notice, be afforded access to, and shall be permitted to audit and copy, the Design-Builder's records and accounts, including complete documentation supporting accounting entries, books, job cost reports, correspondence, instructions, drawings, receipts, subcontracts, Design-Builder's, Contractor's and Subcontractor’s proposals, Design-Builder's, Contractor's and Subcontractor’s invoices, purchase orders, vouchers, memoranda, and other data relating to this Agreement. The Design-Builder shall preserve these records for a period of three (3) years after Final Payment (as defined in Section 9.10.1 of the AIA Document A141–2017) or for such longer period as may be required by law. All records shall be maintained in accordance with generally accepted accounting procedures, consistently applied and in compliance with all applicable laws. Contractors and Subcontractors retained by the Design-Builder on a “cost-plus” basis shall have the same obligations to retain records, books, correspondence, instructions, drawings, receipts, vouchers, memoranda, and any other data relating to the Contract. If the Owner audits the Design-Builder’s books and records and discovers an error in the Owner’s favor, then the Design-Builder shall promptly refund to the Owner any amount overpaid by the Owner. If such error is more two percent (2%) of the Cost of the Work through the date of such audit, then the Design-Builder shall also promptly reimburse the Owner for the cost of such audit. The Design-Builder agrees to include the provisions of this Article A5.5 in all agreements with Subcontractors with respect to any records, accounts and payments relating to the Work and/or the Project, which may be done by an incorporation by reference.

§ A.5.6 Relationship of the Parties

The Design-Builder accepts the relationship of trust and confidence established by this Agreement and covenants with the Owner to exercise the Design-Builder’s skill and judgment in furthering the interests of the Owner; to furnish efficient construction administration, management services and supervision; to furnish at all times an adequate supply of workers and materials; and to perform the Work in an expeditious and economical manner consistent with the Owner’s interests.

This Amendment to the Agreement entered into as of the day and year first written above.

| OWNER (Signature) |  | DESIGN-BUILDER (Signature) |
| --- | --- | --- |
| « Michael Daily, »« Principal » |  | «Jared W. Heald,»« SVP Finance and Legal » |
| (Printed name and title) |  | (Printed name and title) |